## Hurricane Awareness
Plan – define the objectives and outline the steps
Do – implement the activity
Study – analyze the results
Act – apply the results to your next cycle or implement the activity on a full scale
Cycle 1: Release information with teaser
Activity | Who | What | When | How
Plan | Chad | researches/organizes/prepares unique content | by COB 5/18 | SMEs, gov't websites and personal research
Do | Chad | Upload Day 1 content (news/facebook/twitter) | by 9 am 5/21 | via Hootsuite, direct news post
Study | Team | obtain solicited feedback | by 3 pm 5/21 | personal invitation
Act |  | Modified news post at 12pm based on current feedback; after talking through feedback, | COB 5/21 | large changes were made: all information was made available to access rather than releasing day-by-day; the original blog post was edited and made an entry point for remaining information; social media timeline will remain the same - it will draw people in using particular information each day
Cycle 2: Make all information available
Activity | Who | What | When | How
Plan | Chad | researches/organizes/prepares unique content/review feedback | by COB 5/21 | SMEs, gov't websites and personal research
Do | Chad | Upload Day 2 content (facebook/twitter) | by 9 am 5/22 | via Hootsuite
Study | Team | obtain solicited feedback | by 3 pm 5/22 | personal invitation
Act |  | After reviewing feedback, we determined we needed to promote the articles on the website's home page with a banner | COB 5/22 | banners created and uploaded
Cycle 3: Create Homepage Banner
Activity | Who | What | When | How
Plan | Chad | researches/organizes/prepares unique content/review feedback | by COB 5/22 | SMEs, gov't websites and personal research
Do | Chad | Upload Day 3 content (facebook/twitter) | by 9 am 5/23 | via Hootsuite
Study | Team | obtain solicited feedback | by 3 pm 5/23 | personal invitation
Act | Karen/Chad | Added a "banner" to promote; determined content needs to be more local | COB 5/23 | Content made locally relevant
Cycle 4: Create Homepage Banner
Activity | Who | What | When | How
Plan | Karen/Chad | researches/organizes/prepares unique - locally relevant - content | 5/24 am | SMEs, gov't websites and personal research
Do | Karen/Chad | Revise content for local relevance | 5/24 am | via website
Study | Team | obtain solicited feedback | by 3 pm 5/24 | personal invitation
Act | Team | Steps from all four cycles to be utilized going forward | continuing | Through review of steps/learnings for ongoing digital media

## Hurricane Stats
Week 1
Metrics | Visits to news page | Facebook Post Likes | Facebook Post Reach | Facebook Click-through | Twitter Click-through
|  |  |  | (bit.ly) | (ow.ly)
2012-05-21 | 18 | 2 | 16 | 4 | 0
2012-05-22 | 11 | 2 | 12 | 0 | 1
2012-05-23 | 9 | 3 | 15 | 0 | 0
2012-05-24 | 5 | 0 | 14 | 0 | 0
2012-05-25 | 10 | 0 | 11 | 0 | 0
2012-05-26 | 7 |  |  | 0 | 0
2012-05-27 | 4 |  |  | 0 | 0
Pages (Visits) | Supply Kits | Family Plan | Wind Safety | Flood Safety
2012-05-21
2012-05-22 | 7 | 6 | 6 | 6
2012-05-23 | 2 | 2 | 3 | 3
2012-05-24 | 3 | 3 | 2 | 2
2012-05-25 | 3 | 2 | 3 | 3
2012-05-26 | 3 | 4 | 2 | 2
2012-05-27 | 0 | 0 | 1 | 1
Week 2
Metrics | Visits to news page | Facebook Post Likes | Facebook Post Reach | Facebook Click-through | Twitter Click-through
|  |  |  | (bit.ly) | (ow.ly)
2012-05-28 | 2
2012-05-29 | 3
2012-05-30 | 0
2012-05-31 | 0
2012-06-01 | 1
2012-06-02 | 0
2012-06-03 | 0
Pages (Visits) | Supply Kits | Family Plan | Wind Safety | Flood Safety
2012-05-28 | 0 | 0 | 0 | 0
2012-05-29 | 3 | 1 | 0 | 0
2012-05-30 | 0 | 0 | 0 | 0
2012-05-31 | 0 | 0 | 0 | 0
2012-06-01 | 1 | 0 | 0 | 0
2012-06-02 | 0 | 0 | 0 | 0
2012-06-03 | 0 | 0 | 0 | 0

## Env. Health
Plan – define the objectives and outline the steps
Do – implement the activity
Study – analyze the results
Act – apply the results to your next cycle or implement the activity on a full scale
Cycle 1: Edit to improve organization/site map
Activity | Who | What | When | How
Plan | Connie, Karen, Chad, Joseph and Jason | Meet to discuss changes to be made to the EH portion of the website. | 2012-06-01 | input from EH director
| Karen and Chad | Review how other Health Departments organize their EH section/Discuss best practices | 2012-06-04 | Review external websites
Do | Karen and Chad | Create a new sitemap | 6/10-6/13 | Reviewing and discuss better organizational structure
Study | Karen, Chad, Joseph and Jason | Review changes with EH SMEs for their input | June - July 2012 | via meetings
Act | Karen and Chad | Apply changes discussed | week of 8/20 | reorganizing information on website for better user experience
Cycle 2: Edit to improve understandability and cultural relevance by user type. Edit for total clarity. Remove redundancies.
Activity | Who | What | When | How
Plan | Karen, Chad and Jason | Review all information. |  | Using information gleaned from previous cycle. Read/review.
Do | Karen and Chad | Rewrite copy for user relevance |  | Using information gleaned from previous cycle, based on review
Study | Karen, Chad and Jason | Review changes with EH SMEs for their input | 2012-08-02 | via meetings
Act | Karen and Chad | Apply changes discussed | 2012-08-31 | Post new/rewritten information to various pages
Cycle 3: Ensure all forms are current, usable and accessable.
Activity | Who | What | When | How
Plan | Karen, Chad and EH SMEs | Review all forms. | ongoing | Move through website, accessing/evaluating every form.
Do | Karen and Chad | Confirm correct, or obtain new. | underway | Based on review.
Study | Karen, Chad and Miesha | Review changes with EH SMEs for their input | 2012-08-22 | via meetings
Act | Karen and Chad | Apply changes discussed | 2012-08-31 | Upload corrected forms.
Cycle 4: Create process for obtaining updates/corrections.
Activity | Who | What | When | How
Plan | Karen, Chad & EH Managers | Review ongoing update process | week of September 3 | Met with new EH Communications Liaison
Do | Karen and Chad | Create procedure for updates | following meeting | All updates will be provided by EH Communications Liaison
Study | Karen, Chad, EH Managers | Review procedure for accuracy/ease |  | via emails
Act | Karen, Chad & EH Managers | Follow new procedures | ongoing | via email

## EH Stats
| 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-12 | 2012-08-12 | 2012-09-01 | 2012-10-01 | 2012-11-01
Total Site Hits | 4228 | 6209 | 5239 | 5239 | 5879 | 5972 | 5548 | 6530 | 7641 | 8849 | 7226
EH Main Page Hits | 161 | 228 | 395 | 379 | 401 | 308 | 322 | 269 | 268 | 171 | 145
Restaurant Page Hits | 519 | 742 | 834 | 767 | 990 | 807 | 840 | 708 | 980 | 1027 | 839
Restaurant Owners | 147 | 188 | 225 | 244 | 274 | 254 | 254 | 241 | 265 | 267 | 208
Other EH | 297 | 322 | 800 | 991 | 1124 | 504 | 539 | 502 | 299 | 322 | 284

## Immunizations
Plan – define the objectives and outline the steps
Do – implement the activity
Study – analyze the results
Act – apply the results to your next cycle or implement the activity on a full scale
Cycle 1: Create campaign for immunizations - back to school
Activity | Who | What | When | How
Plan | Karen/Chad | research/organize/prepare unique content | by 7/9 | internal SME/existing information
Do | Chad | Back to school immunization information (news/facebook/twitter) | 2012-07-16 | via Hootsuite, direct news post
Study | Karen/Chad | Review metrics - 1222 hits to immunization page | ongoing | google analytics, facebook analytics, etc.
Act | Karen/Chad | Create ongoing immunization campaigns | ongoing | use facebook, twitter, news post, etc. for future immunization campaigns
Cycle 2: Create campaign for immunization awareness month
Activity | Who | What | When | How
Plan | Karen/Chad | research/organize/prepare unique content | by 7/31 | internal SME/CDC info/existing in-house information
Do | Chad | Back to school immunization information (news - 1/facebook & twitter - 7 each) | month long | via Hootsuite, direct news post
Study | Karen/Chad | Review metrics - 841 hits to immunization page | ongoing | google analytics, facebook analytics, etc.
Ah - ha moment | Karen/Chad | Compared July - August immunization metrics. Noticed that immunization numbers for July were MUCH higher than August. Although July only had one post and August had multiple. Performed a thorough, fine-comb review of campaigns - dates, information, posting locations, etc. | 2012-10-12 | Determined that July site hits were more succesful due to one thing: we kept visitors on OUR page. In August, all posts sent visitors to web sites that were not ours. We did not follow our three Change Strategies. We did not (1) create unique content; (2) increase OUR visibility; (3) increase engagement with OUR site
Act | Karen/Chad | Review and Apply Change Strategies to all campaigns | ongoing | CDC site syndication, more unique content. Keep site visitors on OUR page.

## Page-Specific Metrics
Site Area | january^^ | february | march | april | may | june | july | august | september | october | november
health promo | 123 | 220 | 196 | 178 | 188 | 219 | 196 | 226 | 245 | 233 | 205
em prep | 71 | 120 | 87 | 87 | 91 | 96 | 100 | 87 | 92 | 95 | 119
inf disease* | 291 | 328 | 338 | 383 | 420 | 436 | 455 | 564 | 411 | 456 | 370
imm** | 313 | 497 | 538 | 622 | 740 | 872 | 1222 | 841 | 749 | 867 | 672
clin serv^ | 497 | 788 | 488 | 527 | 483 | 548 | 670 | 629 | 754 | 734 | 606
Website Total Pageviews | 4228 | 6209 | 5239 | 5239 | 5879 | 5972 | 5548 | 6530 | 7641 | 8849 | 7226
* includes all epidemiology pages
** includes child, adult, and travel immunization pages
^ includes Family Planning and DNA Lab Testing
^^ dates from Jan 14-Jan 31