DCHS Immunization Data Entry Quality Improvement Project

PLAN

- Team

Jeff Emrick, Cherstin Callon, Heather Kaisner, Kathy Christensen, Holly Nyquist, Jan Walyer, Aylett Wright, and Cindy Barnes.

- Identify the Problem

Immunization data entry was a finding on the Oregon State Immunization Program Triennial Review in May 2010.  The finding was that DCHS immunization data entry did not meet the necessary benchmark of 80% of data being entered into the State IRIS/ALERT database within 14 days of vaccine administration.

AIM Statement: 95% of all immunization administration data from all Deschutes County Public Health clinics will be entered into IRIS/ALERT within 14 days of administration.

- Examine the Current Approach

Current Immunization Workflow:

Baseline Data Entry Jan 08 – Oct 2010

% of Immunization data submitted within 14 days

| Site | 2008 Avg. | 2009 Avg. | 2010 Avg. |
| --- | --- | --- | --- |
| Clinic Lapine | 62% | 61% | 71% |
| Clinic Bend | 65% | 61% | 54% |
| Clinic Redmond | 56% | 46% | 63% |
| SBHC Lapine | 49% | 54% | 57% |
| SBHC Ensworth | 24% | 64% | 67% |
| SBHC Lynch | 14% | 46% | 33% |

Root Cause Analysis

- Identify Potential Solutions

Potential solutions included adding an additional staff member to conduct data entry, develop a consistent courier schedule, and eliminate unnecessary rework and quality checking that result in interruptions of data entry.

- Develop an Improvement Theory

If a regular courier schedule can be established, additional staff can assist with data entry, and we can decrease the number of errors on immunization paperwork, then immunization data entry timeliness will be improved across clinics.

DO

In response to our improvement theory, we conducted four interventions and collected data following a one month period.

- Test the Theory

The following improvements have been made over a one month period in response to our improvement theory:

- We developed and implemented a regular courier schedule.

- Allocated an additional staff member to be trained to complete data entry for the Bend Clinic.

- Front Office staff have been trained to check immunization paperwork for completeness at the time of service to eliminate re-work later.

- Clinicians re-trained to accurately complete paperwork and will be held accountable for errors.

CHECK

- Check the Results

The results for our first data collection, 11/30/2010 are as follows:

| Site | 11/2010 | 11/2009 | 11/2008 |
| --- | --- | --- | --- |
| Clinic Lapine | 0% | 100% | 62% |
| Clinic Bend | 68% | 27% | 39% |
| Clinic Redmond | 78% | 28% | 17% |
| SBHC Lapine | 67% | 32% | 29% |
| SBHC Ensworth | 86% | 86% | 26% |
| SBHC Lynch | 38% | 21% | 27% |

On average, across all clinics, we observed a 31% increase in data entry timeliness.  Given the above results, we determined that our interventions resulted in improvements at the majority of our clinics.  Given that the test period was only one month, we are anticipating additional improvements reflecting at least 50% average improvement across all clinics by our next data collection of 12/31/10.

ACT

- Standardize the Improvement or Develop New Theory

We will adapt our improvement theory by extending the study time and continue with the efforts based on the improvements observed thus far.  With a longer study period and more data we should be able to determine if we should adopt or abandon our improvement efforts.

- Establish Future Plans

We will continue to monitor and collect data until July 1, 2011 at which time we will evaluate the full effectiveness of the changes.  We will monitor data entry rates on a six month basis to ensure the maintenance of our improvements.

# Text boxes

Deschutes County Health Services

2577 NE Courtney Dr.

Bend, OR 97701

(541)322-7400

(The red indicates our identified root causes)