## Slide 1
2012 Quality Improvement
Improving Immunization Process

## Slide 2: Why Quality Improvement?
Health District interest in systematic evaluation and improvement of its programs and processes
Immunization program already tracking administration errors

## Slide 3: Immunizations Project Team
Scott Davis, QI Coordinator TPCHD
Brenda Newell, LICSW HIV/STD/VHO Mgr SHD
Rita Mell, RN, BSN Immunization Mgr SHD
Ivy Giessen, Applications Systems Analyst SHD
Immunization Clinic Staff SHD

## Slide 4: Immunization Project Identification

## Slide 5: Immunization AIM Statement
Reduce the immunization error rate from 1-2/1000 to less than 1/10,000 administrations by 12/31/2012
30% reduction in error rate from 5.3/1000 to 4/1000 administrations by 12/31/2012

## Slide 6
Introduce QI method to staff – buy in
Obtain baseline data
Define error type
Standardize clinic processes
Establish new work flow
Immunization Project Activities

## Slide 7
Immunization Root Cause

## Slide 8
Immunization Tracking
Chart: VPD QI Vaccination Data Quality Report August 2011 - Aug 2012 Administered Doses Source: Washington Immunization Information System (WAIIS)
| 40756 | 40787 | 40817 | 40848 | 40909 | 40940 | 40969 | 41011 | 41041 | 41072 | 41102 | 41133
Total Administered Doses 14,524 | 1425 | 1923 | 1783 | 1220 | 868 | 712 | 1782 | 1101 | 1344 | 906 | 739 | 721

## Slide 9: Immunization Error Type
Chart: VPD QI Vaccination Data Quality Report August 2011 - August 2012 Error Type
| Additional Dose | Wrong Vaccine | Minimum Interval Not Met | Outside Age Range | Anaphylaxis & Repeat Dose | Live Virus & Immunocompromised
Total Errors 77 | 0.61 | 0.21 | 0.13 | 0.05 | 0 | 0

## Slide 10: Immunization Errors

## Slide 11: Aim Statement
30% reduction in error
December 2011, baseline 5.3/1000
January—August 2012:
Total doses = 8,466
Total errors = 22
2.5/1000 error rate
53% reduction in error!

## Slide 12: Next Steps
Continue monthly analysis of doses administered
Calculate error rate
Remediate repetitive errors
Create atmosphere of excellence
Embrace change

## Slide 13
For more information, contact:
Rita Mell, RN, BSN
Phone: 425-339-8626
Email: rmell@snohd.org
www.snohd.org