**Goal/Purpose of the Project:**

The goal of this project is to increase submission and create awareness of quickstrike submission through a promotion event.

**Aim Statement:**

By September 30, 2015, 10 quickstrike projects will be submitted.

**Data (Baseline and Project Completion):**

**Baseline Data:** Submissions for 2015 (to project start date)

|  |  |  |
| --- | --- | --- |
| Quarter 1 | January | 2 submissions |
| February | 1 submission |
| March | 2 submissions |
| Quarter 2 | April | 1 submission |

**Project Completion Data:** Submissions for 2015

|  |  |  |
| --- | --- | --- |
| Quarter 1 | January | 2 submissions |
| February | 1 submission |
| March | 2 submissions |
| Quarter 2 | April | 1 submission |
| May | 0 submissions |
| June | 0 submissions |
| Quarter 3 | July | 0 submissions |
| August\*\* | 15 submissions |
| September | 0 submissions |
| Quarter 4 | October | 1 submission |
| November | 1 submission |
| December | 0 submissions |

**Tools Used for the Project:**

Brainstorm-why low submissions

Nominal Group Technique-address fear of more work (documentation) and forget submission process

**Project Outcomes:**

By September 30, 2015, 21 quickstrike projects were submitted. QI Project Proposal created to replace index card submission.

**Lessons Learned:**

Consider regular “promotion” of submissions-perhaps through monthly staff meeting shout outs, etc.

**Any Visuals to Share:**

