## Slide 1
Team: Right on Time!
Updated April 14, 2015
The Florida Department of Health in Seminole County
Lean Six Sigma
Green Belt Project Objective: To Reduce Client Cycle Time Within the Clinic

## Slide 2
Sponsor: Sarah Wright, MPH, BSN, RN
Sara Warren MPA (lead) Operations Manager
Bertie Barber BSN, RN Community Health Planning Manager
Patrice Boon RN TB-Refugee Health-Immunizations Manager
Dr. Swannie Jett, DrPH, MSc Health Officer
Yellow Belt Certified 100+ Yrs. Clinical Experience
QI Council Chair/Members Multi-Department Team
Team Profile

## Slide 3: Operational Definitions
Cycle Time - Total time from client electronic check-in by staff to client check-out from clinic by staff.
Integrated Clinic – Clinic which provides medical services for multiple programs: Prenatal, STD, Family Planning, Child/Adult Health
Payer - The person or organization responsible for service cost.
Provider – Medical Doctor or Advanced Registered Nurse Practitioner
Short Visit - Visits identified as quick in nature (not requiring clothing removal for exam): Family Planning supply refills, Consultations, School Physicals, Pregnancy Testing, Established Client Prenatal Visit and STD Screening/treatment visits.
State Benchmark - Desired cycle time established by Practice Management Institute.
STD - Sexually Transmitted Disease

## Slide 4
Fiscal year 2014-2015 Health Officer Dr. Swannie Jett requested that the QI Council review the clinical process.
This objective was driven by internal/external customer complaints.
Background
Analyze
Define
Measure
Improve
Control
1.
Clinic End Times July - Sept 2014
Who:
Sara Warren
When:
10/1/14
How:
HMS/EARS
Integrated Clinic
60 Appointments
1.5 Providers / 2 Nurses
1 HST / 1 Support
AVERAGE “SHORT VISIT” CYCLE TIME (all programs) SEP-OCT 2014 = 67 MIN

## Slide 5
Project Selection Matrix
Potential Themes | Importance | Need to Improve | Total Score
Billing Cycle Time | 3 | 2 | 6
Client Cycle Time | 4 | 5 | 20
Eligibility Screening Cycle Time | 4 | 2 | 8
Quick Access to New Patient Appt. | 5 | 2 | 10
Scale: 1 = Negligible 2 = Somewhat 3 = Moderate 4 = Very 5 = Extreme |  |  | 
The team evaluated the components of the clinical process flow for stakeholder impact and need for improvement.
20
The team selected Client Cycle Time due to its impact on the stakeholder groups and identified need for improvement.

## Slide 6: Selected Project Stakeholder Impact
Three stakeholder groups were identified with distinct and overlapping expectations
Stakeholder Group | Expectations
Client | -Clinical needs are met quickly and accurately
Clinical Staff | -Appointment schedule accurately reflects daily client flow -Staff will get out on time -Back-up staff will be available when assist is needed
Senior Management | -No customer complaints -Clients will leave the building on time to maintain security -Clearly defined clinical processes / cross trained staff -Meet state QI requirements and encourage QI culture

## Slide 7: COST OF POOR QUALITY
Stakeholder Group | Cost of Poor Quality
Client | Decreased access to care, low client return rate, increased client frustration
Clinical Staff | Nurses working an average of 1.5 hours past normal business hours per week resulting in an estimated 235 hours requiring flex. A estimated $5,000 yearly impact.
Senior Management | Customer complaints Decreased revenue Low client return rates Poor community image Employee complaints

## Slide 8: Client Short Visit Cycle Times September – October 2014
Minutes
Theme: Reduce client cycle time through clinic for short visits to
the State Benchmark of 45 minutes by March 2015
Who: Sara Warren
When: 10/27/14
How: Sign-In Sheet HMS Check-Out Report
3.
Good
Actual Performance
Target
5.

## Slide 9: Project Planning
Theme: Reduce client cycle time through clinic for short visits to the State benchmark of 45 minutes by March 2015.
Duration: September 2014 – May 2015 (9 months)
4.
PROJECT STEPS | 2014 |  |  |  | 2015 |  |  |  | 
 | S | O | N | D | J | F | M | A | M
DEFINE |  |  |  |  |  |  |  |  | 
MEASURE |  |  |  |  |  |  |  |  | 
ANALYZE |  |  |  |  |  |  |  |  | 
IMPROVE |  |  |  |  |  |  |  |  | 
CONTROL |  |  |  |  |  |  |  |  | 
Projected
Actual
Define
Measure

## Slide 10: Current Process Data Collection September – October 2014
Define
Measure
Staff Training

## Slide 11: Histogram of Client Cycle Times (Short Visit) September – October 2014
Chart: Client Cycle Time (Short) September-October 2014
| 18.5-25.5 | 25.5-32.5 | 32.5-39.5 | 39.5-46.5 | 46.5-53.5 | 53.5-60.5 | 60.5-67.5 | 67.5-74.5 | 74.5-81.5 | 81.5-88.5 | 88.5-95.5 | 95.5-102.5 | 102.5-109.5 | 109.5-116.5 | 116.5-123.5 | 123.5-130.5 | 130.5-137.5 | 137.5-144.5 | 144.5-151.5 | 151.5-158.5 | 158.5-165.5 | 165.5-172.5
 | 14 | 24 | 44 | 59 | 79 | 73 | 55 | 35 | 53 | 26 | 25 | 18 | 17 | 12 | 8 | 7 | 2 | 5 | 4 | 5 | 1 | 4
Define
Measure
75.3% of short visits were longer than 45 minutes!!

## Slide 12: Checksheet - Client Short Visits Sept.-Oct., 2014
Define
Measure
10.
Day of the Week
Staffing Level
Payer Source
Time of Day
New Client
Number of Clients
Check-in vs Apt Time

## Slide 13: Analysis of Stratification By Program
Chart: STD Client Cycle Time (short) Sept-Oct 2014
| 18.5-25.5 | 25.5-32.5 | 32.5-39.5 | 39.5-46.5 | 46.5-53.5 | 53.5-60.5 | 60.5-67.5 | 67.5-74.5 | 74.5-81.5 | 81.5-88.5 | 88.5-95.5 | 95.5-102.5 | 102.5-109.5 | 109.5-116.5 | 116.5-123.5 | 123.5-130.5 | 130.5-137.5 | 137.5-144.5 | 144.5-151.5 | 151.5-158.5 | 158.5-165.5 | 165.5-172.5
 | 8 | 9 | 11 | 11 | 23 | 21 | 7 | 8 | 13 | 6 | 9 | 4 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Chart: Family Planning Client Cycle Time (short) Sept-Oct 2014
| 18.5-25.5 | 25.5-32.5 | 32.5-39.5 | 39.5-46.5 | 46.5-53.5 | 53.5-60.5 | 60.5-67.5 | 67.5-74.5 | 74.5-81.5 | 81.5-88.5 | 88.5-95.5 | 95.5-102.5 | 102.5-109.5 | 109.5-116.5 | 116.5-123.5 | 123.5-130.5 | 130.5-137.5 | 137.5-144.5 | 144.5-151.5 | 151.5-158.5 | 158.5-165.5 | 165.5-172.5
 | 4 | 13 | 22 | 33 | 35 | 36 | 26 | 20 | 20 | 9 | 10 | 8 | 6 | 2 | 1 | 3 | 0 | 1 | 0 | 1 | 1 | 2
Chart: Adult/Child Client Cycle Times (short) Sept-Oct 2014
| 18.5-25.5 | 25.5-32.5 | 32.5-39.5 | 39.5-46.5 | 46.5-53.5 | 53.5-60.5 | 60.5-67.5 | 67.5-74.5 | 74.5-81.5 | 81.5-88.5 | 88.5-95.5 | 95.5-102.5 | 102.5-109.5 | 109.5-116.5 | 116.5-123.5 | 123.5-130.5 | 130.5-137.5 | 137.5-144.5 | 144.5-151.5 | 151.5-158.5 | 158.5-165.5 | 165.5-172.5
 | 0 | 1 | 2 | 5 | 8 | 7 | 14 | 4 | 8 | 4 | 2 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.
Who: Sara Warren
When:
Nov 5, 2014
How:
Client Routers
n: 570 K: 24
R: 153 W: 7
Measure
Define

## Slide 14: Analysis of Stratification by Program
Problem Statement: 81% of Prenatal clients experienced cycle times longer than 45 minutes from check-in to check-out.
Target: Reduce the percentage of Prenatal clients with cycle times greater than 45 minutes by half.
Impact: Reaching target will reduce the overall average cycle time to 60 minutes
7.
8.
11.
9.
6.
Chart: Prenatal Client Cycle Time (short) Oct 2014
| 18.5-25.5 | 25.5-32.5 | 32.5-39.5 | 39.5-46.5 | 46.5-53.5 | 53.5-60.5 | 60.5-67.5 | 67.5-74.5 | 74.5-81.5 | 81.5-88.5 | 88.5-95.5 | 95.5-102.5 | 102.5-109.5 | 109.5-116.5 | 116.5-123.5 | 123.5-130.5 | 130.5-137.5 | 137.5-144.5 | 144.5-151.5 | 151.5-158.5 | 158.5-165.5 | 165.5-172.5
 | 2 | 1 | 9 | 10 | 13 | 9 | 8 | 3 | 12 | 7 | 4 | 5 | 4 | 7 | 5 | 4 | 2 | 4 | 4 | 4 | 0 | 1
n: 570 K: 24
R: 153 W: 7
Who: Sara Warren
When:
Nov 5, 2014
How:
Client Routers
Measure
Define

## Slide 15
Cause and Effect Diagram
Define
Analyze
Our Cause and Effect Analysis Revealed 3 Potential Root Causes
110 Steps to Provide Chart
Duplicate Charting
Inadequate Appt. Time

## Slide 16: Probable Root Cause Verification
Define
Analyze
Three verified root causes were identified
14.

## Slide 17: Probable Cause Verification Matrix
Define
After data analysis three root causes were identified regarding client cycle times.
Time studies were conducted on prenatal clients to determine time wasted on root cause issues. This enabled the team to estimate the impact of each root cause on the gap.
The sponsor signed off on the define, measure and analyze steps of this project.
14.
15.
16.
Improve
5. ,
11. ,

## Slide 18: Countermeasures Matrix
Define
Analyze
Three Countermeasures Identified
18.
17.
Improve

## Slide 19: Countermeasures Matrix
Define
Improve
Three Countermeasures Identified

## Slide 20: Countermeasures Matrix
Define
Improve
Three Countermeasures Identified

## Slide 21: Barriers and Aids Analysis
Define
Barriers and Aids Analysis was conducted on the 3 selected Practical Methods
19.
Improve

## Slide 22: Barriers and Aids Analysis
Improve
Define

## Slide 23: Action Plan
Analyze
Define
Improve
Action plan was implemented with sponsor approval.
20.

## Slide 24: Overall Impact of Countermeasures During Pilot
Improve
Define
Before
After
Average Cycle Time was reduced from 67 to 53 minutes
75% of all visits were over 45 minutes
58% of visits were over 45 minutes
21% reduction
21.
Benchmark
Average
Old Average
Benchmark
New Average

## Slide 25: Overall Impact of Countermeasures During Pilot
Improve
Define
Before with Prenatal as short visit
After w/o Prenatal
Average Cycle Time (w/o Prenatal “short” visit) reduced from 67 to 47 minutes
Benchmark
Average
Countermeasure #3
Change Clinic Schedule
New Average
Old Average
Benchmark

## Slide 26: Evaluation / Standardization
Discussion and input from operations/clinical staff regarding pilot period. Identification of next step action plan.
Define
Improve

## Slide 27: Evaluation / Standardization
Lessons Learned & Future Plans:
1- Since clinical service may change based on needs of the community, keep updated data to ensure understanding of clinic flow.
2- Changes to process flow require subsequent review and revisions to internal operational forms.
3- It is helpful to ensure continuous communication between operations, clinical and billing staff through establishment of standing quarterly joint meetings.
4- Decreased duplicate charting has also resulted in the cost savings of fewer charts purchased and/or ordered from storage.
5- Keep an open mind. The story continues!
The Sponsor signed off on project action plan and expected results!
Define
23.
22.
Improve

## Slide 28: Evaluation / Standardization
Impact on Indicator
Define
23.
22.
Good
Who: Sara Warren
When: 3/30/15
How: HMS Sign-in /Out Report / Routers
Since implementation of countermeasures, time studies have been conducted on a random sampling (10%) of client cycle times. Average cycle time since implementation is currently 46 minutes.
Improve