## Action List
Team: PAP Corner Blues | [5 empty] | Date: April 15, 2011
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
1 | Revisit who reviews lab log for overdue lab results, when to review, what to do with findings, how many weeks old will be considered as late? | Debbie S, Michelle | 2011-05-01 | 0% | 100% | Lab Manager to check each Friday and sign lab sheet that all labs are completed. State lab will have 4-6 weeks. Wilks Lab will have 2 weeks.
2 | Contact Lab Consultant to see if it must be the Lab Mgr or if whoever reviews the log can initial the sheet as not making a medical decision from this review. | Debbie S, Michelle | 2011-05-01 | 0% | 100% | Main lab tech will sign top of sheet. If other lab techs do a lab, they will initial client sticker to indicate who performed that lab.
3 | Determine if standing orders can be created'used for review of lab results to move normals to records and abnormals to FNP quicker and with fewer handoffs. | Martha, Michelle, Debbie S. | 2011-05-01 | 0% | 100% | Lab manager will sign each lab received per state consultant
4 | Determine if within 14 day patient notification should remain or should it be tightened based on results of changes | Lisa, Team | 2011-06-30 | 0% | 100% | Only a maternity case in Nov prevented Sept thru Jan data to be under 5 days.
5 | Determine if we should continue the patient survey in the present format. | Lisa, Eva Avalos, Marisol Rubio | 2011-06-30 | 50% | 50% | Lisa I will give list to interpreters to call clients monthly.
6 | Redo all of the "1/2 sheet" based on FP model reviewed on 4/5 | Alice | 2011-04-18 | 0% | 100% | To begin use on 4/18/11
7 | Rewrite the policy for the handling and notification of PAP results and gain approval to implement including Dr. McGrath's approval | Lisa, Martha, Monecia, Debbie D | 2011-08-01 | 0% | 100% | Policy amended for transferring clients. BOH approved 5/17/11. HD, County Atty, Nurse Sup, MD must sign before policy can be used.
8 | Have IT review lab computer for issue of locking up when entering HIS. Goal to to use system for medicaid number look up when needed for the lab label. | Monecia | 2011-05-01 | 0% | 100% | Agency policy states that computers will time out and a password will be needed.
9 | Determine if an electronic registry program would be a good substitute for Lisa's "tracking calendar" for followups. | Lisa | 2011-06-30 | 55% | 45% | Request made to IT on 4/4/11. No response from IT yet. Anitra from WCHD is forwarding information about their system.
10 | Eliminate use of PAP log in all new charts | YCHD staff | 2011-04-14 | 0% | 100% | No longer using Pap log
11 | Move existing PAP logs to end of PAP tabbed section in medical records. Do as charts are being worked. | YCHD staff | On-going | 0% | 100% | Met with staff 4/14/11. Will move existing Pap logs at each client encounter. New clients will not include pap log
12 | Standing Order for Abnormal Pap's and Treatment options for infection found on Pap | Martha, Debbie D | 2011-08-01 | 0% | 100% | Standing Orders completed. Awaiting Medical Director's signature.
13 | Update Adult Health/FP history forms | Lisa | 2011-06-30 | 50% | 50% | Waiting until after WH audit. Lisa to speak with Pat Horton after audit.
14 | Steno pad removal with team review | Debbie S, Lisa | 2011-06-30 | 100% | 0% | Will continue to use for now. Re-assess at 6/30/11
15 | Red stamp for abnormal pap tag, standing order notebook with tabs and lab log notebook | Martha | 2011-05-01 | 0% | 100%
16 | Colpo to be entered in history/surgeries on problem list. Pap results and follow up to acute problems section on problem list. | Lisa | 2011-04-14 | 0% | 100% | Communication to Staff on 4/14/11. Effective immediatley
17 | Staff Survey after implementation of changes | Lisa | 2011-05-01 | 0% | 100% | Satisfacation noted with changes
18 | Continue obtaining data on Run Chart for # if das between Pap RTN from lab and client notification | Lisa | 2011-09-30 | 50% | 50% | To include: # of days between Pap RTN from Lab and Client notification
18 | Add Clients financial responsibility on Pap Letters (A,B,C,D) both english and spanish | Lisa | 2011-04-14 | 0% | 100% | Letters saved on Lisa I. computer.
19 | Update Chart Order/Remove Pap log/move established clients pap log to last page under pap tab | Trish | 2011-05-01 | 0% | 100% | POHR-Problem Oriented Health Record. Completed 4/18/11
20 |  |  |  | 100% | 0%
21 |  |  |  | 100% | 0%
22 |  |  |  | 100% | 0%
23 |  |  |  | 100% | 0%
24 |  |  |  | 100% | 0%
25 |  |  |  | 100% | 0%
26 |  |  |  | 100% | 0%
27 |  |  |  | 100% | 0%
28 |  |  |  | 100% | 0%
29 |  |  |  | 100% | 0%
30 |  |  |  | 100% | 0%
31 |  |  |  | 100% | 0%
32 |  |  |  | 100% | 0%
33 |  |  |  | 100% | 0%
34 |  |  |  | 100% | 0%
35 |  |  |  | 100% | 0%
36 |  |  |  | 100% | 0%
37 |  |  |  | 100% | 0%
38 |  |  |  | 100% | 0%
39 |  |  |  | 100% | 0%
40 |  |  |  | 100% | 0%
| Put in formula, value in col E and F, insert the pie chart into G, select data by choosing E and F, format colors and outline on the pie. |  |  | 90% | 10%
| Value = sum(1-Fxx) |  |  | 60% | 40%

## Parking Lot
Parking Lot for | [5 empty] | Date
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
1 |  |  |  | 100% | 0%
2 |  |  |  | 100% | 0%
3 |  |  |  | 100% | 0%
4 |  |  |  | 100% | 0%
5 |  |  |  | 100% | 0%
6 |  |  |  | 100% | 0%
7 |  |  |  | 100% | 0%
8 |  |  |  | 100% | 0%
9 |  |  |  | 100% | 0%
No. | Action/Suggestion/ Recommendation | Person Responsible | Date/Time Due | % Not Complete | % Complete | Resolution/Status
10 |  |  |  | 100% | 0%
11 |  |  |  | 100% | 0%
12 |  |  |  | 100% | 0%
13 |  |  |  | 100% | 0%
14 |  |  |  | 100% | 0%
15 |  |  |  | 100% | 0%
16 |  |  |  | 100% | 0%
17 |  |  |  | 100% | 0%
18 |  |  |  | 100% | 0%